## Overview
NEXUS — Personal Agent OS · One-Month Work Breakdown Structure (WBS)
Two-mode orchestrator (Developer + Personal) driving Claude Code & Codex over subscriptions. Built in 4 versions across 4 weeks.
HOW TO READ THIS WORKBOOK
Overview | This page — scope, schedule, legend, how the sheets fit together.
WBS by Feature | The core sheet. Every version is broken into FEATURES; every feature into concrete build tasks with what it delivers, tools, dependencies, effort, and Definition of Done.
Daily Plan (Month) | Day-by-day execution calendar — 20 working days (Mon-Fri x 4 weeks). What to actually sit down and do each day.
Feature Summary | One row per feature: a high-level rollup with total effort and the week it lands.
THE PLAN AT A GLANCE
Week 1 · v0.1 — One task, run in the background | Prove the magic: submit a task, walk away, watch Claude & Codex duel in sandboxes, get annotated self-verified diffs + a judge's pick.
Week 2 · v0.2 — The overnight loop | Make it durable & unattended: Temporal workflow, retry-on-failure, job queue, Telegram approve-from-phone, minimal quota governor, always-on box.
Week 3 · v0.3 — Repo brain & triggers | Make it smart & trustworthy: tree-sitter repo knowledge graph, memory, independent second-model reviewer, auto-triggers (CI-fail -> fix plan), Langfuse tracing.
Week 4 · v0.4 — Personal mode & hardening | Add the second half: Gmail/Calendar/Notion Personal Mode on a local model, full cost governor, eval harness, safety hardening (two-key, privacy firewall, vault).
HOW TO USE IT
Feature-first | Read a feature row to understand WHAT you're building and WHY, then the task rows under it for HOW. Design decisions live in Research.md; buildable specs in context/v0.x.
Track progress | Use the Status column dropdown (Not started / In progress / Blocked / Done) on the WBS and Daily sheets. Filter or colour-sort to see where you are.
Effort is a solo estimate | Hours assume one focused developer. The 4-week pace is AGGRESSIVE for all four versions — treat week boundaries as milestones, and stretch to 6-8 weeks if a version needs it. Ship each version before starting the next.
Source of truth | Where this WBS and a version doc disagree, the version doc wins (context/nexus-v0.x-*.md). Acceptance criteria there are the real gates.

## WBS by Feature
WBS BY FEATURE — Nexus (v0.1 -> v0.4, one month)
WBS ID | Wk | Day(s) | Version | Feature | Task / Work Item | What it delivers | Key tools / tech | Depends on | Hrs | Definition of Done | Status
1.1.1 | 1 | Day 1 | v0.1 | Environment & CLI proof | Install Docker Desktop (WSL2 backend) | Local sandbox runtime ready; repo clones kept inside WSL2 fs | Docker, WSL2 | - | 3 | docker run hello-world works; WSL2 backend confirmed | Not started
1.1.2 | 1 | Day 1 | v0.1 | Environment & CLI proof | Confirm claude -p and codex exec run headless by hand | Proof the core magic works before any code | Claude Code, Codex CLI | 1.1.1 | 3 | Both CLIs return structured JSON from a real prompt in the terminal | Not started
1.1.3 | 1 | Day 1 | v0.1 | Environment & CLI proof | Stand up Postgres+Redis via db/docker-compose.yml; apply 0001_core.sql | Data layer live with the core schema | Postgres, Redis | 1.1.1 | 2 | Tables in core.* exist; app can connect | Not started
1.2.1 | 1 | Day 2 | v0.1 | CodingAgentAdapter | Define CodingAgentAdapter protocol (base.py) | Uniform run(task,repo,cwd)->Result interface, swappable backend | Python | 1.1.2 | 2 | Protocol + Result dataclass defined and typed | Not started
1.2.2 | 1 | Day 2 | v0.1 | CodingAgentAdapter | Implement claude_cli + codex_cli backends | Shell out to official CLIs as subprocesses (no API, no OAuth hacks) | subprocess, Claude/Codex | 1.2.1 | 4 | Each backend returns diff + log + summary for a real task | Not started
1.2.3 | 1 | Day 2 | v0.1 | CodingAgentAdapter | Optional ollama backend (free brain / judge) | Zero-cost fallback + judge path | Ollama, Qwen3-Coder | 1.2.1 | 2 | Ollama backend runs a task locally end to end | Not started
1.3.1 | 1 | Day 2-3 | v0.1 | Sandbox | Build nexus-sandbox image (git + CLIs + toolchains) | Reproducible container to run agents in | Docker | 1.1.1 | 3 | Image builds; claude/codex/git available inside | Not started
1.3.2 | 1 | Day 3 | v0.1 | Sandbox | Container lifecycle: create -> clone -> fresh branch -> diff -> destroy | Real files never touched; each run isolated | Docker, git | 1.3.1 | 4 | A run produces a diff on a fresh branch; host tree untouched (git status clean) | Not started
1.4.1 | 1 | Day 3 | v0.1 | Backend API + storage | FastAPI POST /task, GET /task/{id}, /repos | Queue a task, read status/diffs, register repos | FastAPI, asyncpg | 1.1.3 | 4 | POST returns task_id+runs; GET returns task/runs/diff | Not started
1.4.2 | 1 | Day 3 | v0.1 | Backend API + storage | pipeline.py: sandbox -> CLI -> verify -> annotate -> judge | Orchestrates a full single run | Python | 1.4.1,1.3.2 | 3 | One submitted task runs the full pipeline to a stored result | Not started
1.5.1 | 1 | Day 4 | v0.1 | Live progress stream | events.py: normalise CLI JSON -> run_events + Redis publish | Every file read / command becomes a stored, streamable event | Redis, Postgres | 1.4.2 | 3 | CLI output lands as core.run_events rows and Redis messages | Not started
1.5.2 | 1 | Day 4 | v0.1 | Live progress stream | WS /task/{id}/stream with replay (?since) + live | Watch it think live; reopen replays identical history | WebSocket, Redis | 1.5.1 | 3 | Events appear <2s; reopening replays full history seamlessly | Not started
1.6.1 | 1 | Day 4 | v0.1 | Multi-brain duel + judge | Duel path: two sandboxes run claude & codex in parallel | Same task, two brains, two branches at once | Docker, asyncio | 1.4.2 | 3 | ['claude','codex'] yields two parallel runs + two diffs | Not started
1.6.2 | 1 | Day 4 | v0.1 | Multi-brain duel + judge | Judge pass: compare both diffs vs the ask -> winner + reasoning | AI recommendation of the better diff | Claude/Codex/Ollama | 1.6.1 | 2 | One judgment row with winner_run_id + reasoning; user override persisted | Not started
1.7.1 | 1 | Day 5 | v0.1 | Self-verification + diff intelligence | Read-only verifier: diff vs original prompt -> {verdict,findings} | Catches 'looks done but isnt' before you see it | Claude/Codex (read-only) | 1.4.2 | 3 | A do-nothing run on 'add validation' yields verdict=fail | Not started
1.7.2 | 1 | Day 5 | v0.1 | Self-verification + diff intelligence | Diff annotation: summary, risk flags, tests touched | Plain-English diff instead of raw patch | LLM pass | 1.7.1 | 2 | diff_annotations row with summary + risk_flags + tests_touched | Not started
1.8.1 | 1 | Day 5 | v0.1 | One-page React UI | Task box, repo dropdown, brain selector, Run | Submit a task from your own UI | React, Vite | 1.4.1 | 3 | Can submit Claude / Codex / Both from the page | Not started
1.8.2 | 1 | Day 5 | v0.1 | One-page React UI | Live stream panel(s) + side-by-side diff viewer + verdict | Watch runs live; compare diffs; see judge pick | React, WebSocket | 1.8.1,1.5.2,1.6.2 | 4 | Duel shows two streams + side-by-side diffs + verdict; override works | Not started
2.1.1 | 2 | Day 6 | v0.2 | Durable loop (Temporal) | Stand up Temporal (own compose stack + DB); apply 0002 migration | Durability engine live | Temporal, Postgres | 1.8.2 | 3 | Temporal UI reachable; schema 0002 applied | Not started
2.1.2 | 2 | Day 6-7 | v0.2 | Durable loop (Temporal) | Port v0.1 single run into one TaskWorkflow (activities) | Run survives crashes; resumes from last activity | Temporal SDK | 2.1.1 | 5 | Kill worker mid-run -> resumes, no duplicate side effects | Not started
2.2.1 | 2 | Day 7 | v0.2 | Retry-on-test-failure | run_tests failure feeds back into a fresh run_brain (max 3) | Agent retries instead of giving up | Temporal | 2.1.2 | 4 | Failing suite -> <=3 linked runs (parent_run_id chain), then asks | Not started
2.3.1 | 2 | Day 8 | v0.2 | Job queue + single-writer lock | Postgres queue (priority, queued_for) + worker pull | Assign tasks before bed; worker drains them | Postgres, Redis | 2.1.2 | 3 | Worker pulls tasks by priority/queued_for | Not started
2.3.2 | 2 | Day 8 | v0.2 | Job queue + single-writer lock | Redis repo lock nexus:lock:repo:{id} + git worktrees | No two agents touch one repo at once | Redis, git | 2.3.1 | 3 | Two tasks/same repo never run concurrently; different repos do | Not started
2.4.1 | 2 | Day 8 | v0.2 | Telegram bot | Bot for notifications (ops.notifications) | Results & questions pushed to your phone | Telegram Bot API | 2.1.2 | 2 | Run result arrives as a Telegram message | Not started
2.5.1 | 2 | Day 9 | v0.2 | Approval gates (signals) | request_approval activity -> ops.approvals + Telegram card | Workflow blocks safely for hours awaiting you | Temporal signals | 2.4.1 | 4 | Approve/Reject from phone resumes/ends the workflow | Not started
2.5.2 | 2 | Day 9 | v0.2 | Approval gates (signals) | Bind approval to params_hash + expires_at | Tamper-proof, expiring approvals | Python | 2.5.1 | 2 | Tampered params refused (hash mismatch); expired = rejected, no hang | Not started
2.6.1 | 2 | Day 10 | v0.2 | Minimal quota governor | Count runs + token est into ops.quota_ledger + Redis counters | Overnight loop can't silently burn a whole window | Redis, Postgres | 2.1.2 | 3 | Usage recorded per premium run in the ledger | Not started
2.6.2 | 2 | Day 10 | v0.2 | Minimal quota governor | Near-cap -> route to free local brain or park task | Degrades gracefully instead of stalling | Ollama | 2.6.1 | 3 | Forced >=cap routes new tasks to local brain (verified in ledger) | Not started
2.7.1 | 2 | Day 10 | v0.2 | Always-on deployment | Deploy full stack to always-on box (restart: unless-stopped) | 'While I sleep' becomes real | Docker Compose | 2.5.1,2.6.2 | 3 | Stack starts on boot on the always-on machine | Not started
2.7.2 | 2 | Day 10 | v0.2 | Always-on deployment | Overnight demo: 3 tasks @23:00 -> morning digest | End-to-end proof of the headline promise | (whole stack) | 2.7.1 | 2 | Wake to 2 PRs + 1 question, all approvable from phone | Not started
3.1.1 | 3 | Day 11 | v0.3 | Repo knowledge graph | Apply 0003; tree-sitter parse -> repo_kg.* relational mirror | Deterministic map of code (funcs/classes/imports/calls) | tree-sitter, Postgres | 2.7.2 | 5 | Full index of a ~50k-LOC repo completes in minutes | Not started
3.1.2 | 3 | Day 12 | v0.3 | Repo knowledge graph | Derive Apache AGE graph; ship rebuild_graph(repo_id) | Multi-hop queries; graph is a rebuildable derived index | Apache AGE | 3.1.1 | 4 | Drop graph -> rebuild_graph restores identical results | Not started
3.1.3 | 3 | Day 12 | v0.3 | Repo knowledge graph | Incremental re-index (XXH3 hash; changed files only) | Fast updates; one-file edit re-parses one file | watchdog, XXH3 | 3.1.1 | 3 | One-file edit re-indexes only that file (last_indexed_at) | Not started
3.2.1 | 3 | Day 13 | v0.3 | Embeddings + hybrid retrieval | Embed code chunks (nomic-embed) into pgvector | Semantic recall over code | pgvector, Ollama | 3.1.1 | 3 | code_chunks embedded and searchable | Not started
3.2.2 | 3 | Day 13 | v0.3 | Embeddings + hybrid retrieval | Hybrid order: vector top-k -> AGE expand -> rerank -> top_k | Precise context, not raw file dumps | pgvector, AGE | 3.2.1,3.1.2 | 3 | Planner gets <=12 reranked chunks, never file dumps | Not started
3.3.1 | 3 | Day 14 | v0.3 | Repo-graph tools | where_is / explain_repo / impact_of_change / risky_files | Agent knows the code before touching it | MCP, Python | 3.2.2 | 4 | impact_of_change on a hot fn: correct callers/tests <200ms p95 | Not started
3.3.2 | 3 | Day 14 | v0.3 | Repo-graph tools | why_does_this_test_fail(test, trace) | Traces failing test -> guilty function/commit | MCP, git blame | 3.3.1 | 3 | Names the guilty commit/function on a seeded regression | Not started
3.4.1 | 3 | Day 13 | v0.3 | Memory | Explicit + episodic memory (memory.facts / episodes) | Remembers across nights | pgvector, Postgres | 3.1.1 | 3 | 'Remember X' retrievable next session | Not started
3.4.2 | 3 | Day 13 | v0.3 | Memory | User controls: remember / forget / correct / show-what-you-know | First-class, audited memory control | Python | 3.4.1 | 2 | 'forget X' -> gone from retrieval immediately; nulled after grace | Not started
3.5.1 | 3 | Day 15 | v0.3 | Independent reviewer | Reviewer step, enforce reviewer_brain != writer_brain | Stop grading its own homework | Temporal | 2.2.1 | 3 | Reviewer read-only; block loops back to writer within retry cap | Not started
3.6.1 | 3 | Day 15 | v0.3 | Trigger engine | ops.triggers (YAML DSL) + dedup (Redis + unique firings) | Autonomy: notices and acts without you queuing | Python, Redis | 2.5.1 | 4 | Triggers match + fire exactly once (dedup on webhook replay) | Not started
3.6.2 | 3 | Day 15 | v0.3 | Trigger engine | GitHub CI-failure webhook -> overnight autoplan (still gated) | CI fails at 2am -> fix plan by morning | GitHub webhooks | 3.6.1 | 3 | Forced night CI fail -> drafted fix plan + review + approval card | Not started
3.7.1 | 3 | Day 14 | v0.3 | Observability (Langfuse) | Self-host Langfuse; trace every workflow step | Replay exactly what the agent saw | Langfuse | 2.1.2 | 3 | One overnight run = one connected trace | Not started
3.7.2 | 3 | Day 14 | v0.3 | Observability (Langfuse) | Route every tool call into audit.log | Append-only accountability | Postgres | 3.7.1 | 2 | Every MCP call/CLI run recorded in audit.log | Not started
4.1.1 | 4 | Day 16 | v0.4 | Personal mode + integrations | Apply 0004; Gmail + Calendar + Notion integrations (free APIs) | Email/calendar/notes reachable | Gmail/Calendar/Notion API | 3.7.2 | 5 | Read calendar, unread mail, Notion pages from Personal mode | Not started
4.1.2 | 4 | Day 17 | v0.4 | Personal mode + integrations | Personal agents: chief-of-staff, inbox-triage, scheduler, curator | The morning chief-of-staff pool (<=8 tools each) | Python, MCP | 4.1.1 | 5 | Agents route intents and compose a briefing | Not started
4.2.1 | 4 | Day 17 | v0.4 | Local brain + mode isolation | Run Personal mode on local Gemma 12B via Ollama | Private comms never leave the machine | Ollama, Gemma | 4.1.1 | 3 | Personal tasks complete on the local model | Not started
4.2.2 | 4 | Day 17 | v0.4 | Local brain + mode isolation | Two DB roles (nexus_dev_mode / nexus_personal_mode); router picks pool | DB-enforced isolation of dev vs personal data | Postgres roles | 4.2.1 | 3 | dev role cannot SELECT personal.*; no secret leaks into dev prompts | Not started
4.3.1 | 4 | Day 18 | v0.4 | Full cost/rate governor | Per-task cost forecasting from similar past runs | Know a task's draw before starting it | Redis, Postgres | 2.6.2 | 3 | Forecast shown pre-run | Not started
4.3.2 | 4 | Day 18 | v0.4 | Full cost/rate governor | Surface '~3 premium tasks left' + per-mode budgets | Personal mode can't starve an overnight dev run | Redis | 4.3.1 | 3 | UI + briefing surface remaining budget; per-mode caps hold | Not started
4.4.1 | 4 | Day 18 | v0.4 | Eval / regression harness | Promote golden tasks; replay + LLM-judge scoring in Langfuse | Upgrade models/prompts with confidence, not hope | Langfuse | 3.7.1 | 4 | Two config_labels scored comparably on a golden task | Not started
4.5.1 | 4 | Day 19 | v0.4 | Safety hardening | Two-key for destructive ops (typed challenge phrase) | Force-push/bulk-delete need a second explicit confirm | Python | 2.5.2 | 3 | force-push without typed phrase refused even after button-approve | Not started
4.5.2 | 4 | Day 19 | v0.4 | Safety hardening | Privacy firewall: classifier strips secrets/PII before cloud calls | Nothing sensitive leaks to a cloud model | Gemma classifier | 4.2.1 | 4 | Planted API key redacted before cloud call; logged in audit.log | Not started
4.5.3 | 4 | Day 19 | v0.4 | Safety hardening | Vault (Infisical / SOPS+age) + command allowlist | Scoped, audited secrets; dangerous commands blocked | Infisical/SOPS | 4.5.1 | 3 | Secrets scoped & never in prompts; rm -rf / .env reads blocked | Not started
4.6.1 | 4 | Day 20 | v0.4 | Voice (optional polish) | Whisper.cpp STT + Piper TTS | Spoken briefing + voice task assignment | Whisper.cpp, Piper | 4.1.2 | 3 | Briefing can be spoken; a voice note becomes a task | Not started
4.7.1 | 4 | Day 20 | v0.4 | Briefing + final acceptance | 7am briefing: calendar + VIP unread + commitments <=48h | The morning chief-of-staff goes live | cron, Telegram | 4.1.2 | 3 | Briefing arrives 7am with correct content | Not started
4.7.2 | 4 | Day 20 | v0.4 | Briefing + final acceptance | Fresh-machine setup test from docs alone (shareable-later) | Another person reaches working v0.1 unaided | docs | 4.7.1,2.7.2 | 3 | Clean setup from repo docs reaches a working v0.1 flow | Not started

## Daily Plan (Month)
DAILY EXECUTION PLAN — 20 working days (Mon-Fri x 4 weeks)
Day | Date | Week / Version | Focus | What to execute today | Status
1 | Mon 06 Jul | Week 1 · v0.1 | Environment & CLI proof | Install Docker (WSL2). Confirm claude -p and codex exec run headless by hand. Bring up Postgres+Redis; apply 0001_core.sql. GATE: prove the magic before writing UI. | Not started
2 | Tue 07 Jul | Week 1 · v0.1 | Adapter + sandbox image | Define CodingAgentAdapter protocol; implement claude & codex (and optional ollama) backends. Build the nexus-sandbox Docker image. | Not started
3 | Wed 08 Jul | Week 1 · v0.1 | Sandbox lifecycle + API | Container create->clone->branch->diff->destroy (host tree untouched). FastAPI POST/GET /task + /repos; wire pipeline.py for one full run. | Not started
4 | Thu 09 Jul | Week 1 · v0.1 | Live stream + duel + judge | events.py -> run_events + Redis; WS stream with ?since replay. Duel path (two parallel sandboxes) + judge pass. | Not started
5 | Fri 10 Jul | Week 1 · v0.1 | Verify, annotate, UI -> SHIP v0.1 | Self-verifier + diff annotation. One-page React UI: brain selector, live panels, side-by-side diff + verdict. Milestone: v0.1 done. | Not started
6 | Mon 13 Jul | Week 2 · v0.2 | Temporal + port run | Stand up Temporal (own stack); apply 0002. Port the v0.1 run into one crash-safe TaskWorkflow of activities. | Not started
7 | Tue 14 Jul | Week 2 · v0.2 | Retry loop | Finish workflow port. Add retry-on-test-failure (max 3, parent_run_id lineage) feeding failures back to the writer. | Not started
8 | Wed 15 Jul | Week 2 · v0.2 | Queue + lock + Telegram | Postgres job queue (priority/queued_for) + worker. Redis single-writer repo lock + worktrees. Telegram bot for notifications. | Not started
9 | Thu 16 Jul | Week 2 · v0.2 | Approval gates | request_approval as a Temporal signal -> ops.approvals + Telegram card. Bind to params_hash + expires_at (tamper-proof, expiring). | Not started
10 | Fri 17 Jul | Week 2 · v0.2 | Governor + deploy -> SHIP v0.2 | Minimal quota governor (ledger + Redis + local fallback). Deploy to always-on box. Overnight demo: 3 tasks @23:00 -> morning digest. Milestone: v0.2 done. | Not started
11 | Mon 20 Jul | Week 3 · v0.3 | Repo KG mirror | Apply 0003. tree-sitter parse pipeline -> repo_kg.* relational mirror (source of truth). Full-index a real repo. | Not started
12 | Tue 21 Jul | Week 3 · v0.3 | AGE graph + incremental | Derive Apache AGE graph; ship rebuild_graph(repo_id). Incremental re-index by XXH3 content hash (changed files only). | Not started
13 | Wed 22 Jul | Week 3 · v0.3 | Embeddings + memory | Embed code chunks into pgvector; hybrid retrieval (vector->graph->rerank). Explicit + episodic memory with user controls. | Not started
14 | Thu 23 Jul | Week 3 · v0.3 | Repo tools + Langfuse | Expose where_is / impact_of_change / risky_files / why_does_this_test_fail. Self-host Langfuse; trace every step; route tool calls to audit.log. | Not started
15 | Fri 24 Jul | Week 3 · v0.3 | Reviewer + triggers -> SHIP v0.3 | Independent reviewer (reviewer_brain != writer_brain). Trigger engine + GitHub CI-fail webhook -> gated autoplan (exactly-once). Milestone: v0.3 done. | Not started
16 | Mon 27 Jul | Week 4 · v0.4 | Personal integrations | Apply 0004. Gmail + Calendar + Notion integrations on free APIs; read calendar/unread/pages from Personal mode. | Not started
17 | Tue 28 Jul | Week 4 · v0.4 | Agents + isolation | Personal agents (chief-of-staff, triage, scheduler, curator) on local Gemma. Two DB roles + router pool selection (DB-enforced isolation). | Not started
18 | Wed 29 Jul | Week 4 · v0.4 | Governor + eval | Full cost governor: per-task forecasting, '~3 left' surfacing, per-mode budgets. Eval/regression harness (golden tasks -> Langfuse scoring). | Not started
19 | Thu 30 Jul | Week 4 · v0.4 | Safety hardening | Two-key for destructive ops (typed challenge). Privacy firewall (redact secrets/PII before cloud). Vault + command allowlist. | Not started
20 | Fri 31 Jul | Week 4 · v0.4 | Voice + briefing -> SHIP 1.0 | Optional Whisper/Piper voice. 7am briefing live. Fresh-machine setup test from docs alone. Milestone: v0.4 = Nexus 1.0. | Not started

## Feature Summary
FEATURE SUMMARY — rollup by feature
Version | Week | Feature | # Tasks | Est. hrs | One-line goal
v0.1 | 1 | Environment & CLI proof | 3 | 8 | Prove claude -p / codex exec work headless before building anything.
v0.1 | 1 | CodingAgentAdapter | 3 | 8 | One swappable interface over Claude/Codex/Ollama via official CLIs.
v0.1 | 1 | Sandbox | 2 | 7 | Isolated Docker run per task; your real files never touched.
v0.1 | 1 | Backend API + storage | 2 | 7 | FastAPI + Postgres to queue tasks and store every run.
v0.1 | 1 | Live progress stream | 2 | 6 | Watch agents think live; replay any run from history.
v0.1 | 1 | Multi-brain duel + judge | 2 | 5 | Race Claude vs Codex on one task; AI judge picks a winner.
v0.1 | 1 | Self-verification + diff intelligence | 2 | 5 | Auto-check the diff vs your ask; annotate risk & tests.
v0.1 | 1 | One-page React UI | 2 | 7 | Submit, watch, and compare diffs from your own UI.
v0.2 | 2 | Durable loop (Temporal) | 2 | 8 | Crash-safe workflow that survives multi-hour overnight runs.
v0.2 | 2 | Retry-on-test-failure | 1 | 4 | Feed test failures back to the agent instead of giving up.
v0.2 | 2 | Job queue + single-writer lock | 2 | 6 | Queue nightly tasks; never two agents on one repo.
v0.2 | 2 | Telegram bot | 1 | 2 | Push results/questions to your phone.
v0.2 | 2 | Approval gates (signals) | 2 | 6 | Block safely for hours; approve from bed; tamper-proof.
v0.2 | 2 | Minimal quota governor | 2 | 6 | Don't burn a whole quota window overnight; fall back to local.
v0.2 | 2 | Always-on deployment | 2 | 5 | Run the stack on an always-on box; the 'while I sleep' promise.
v0.3 | 3 | Repo knowledge graph | 3 | 12 | tree-sitter AST map of your code for multi-hop questions.
v0.3 | 3 | Embeddings + hybrid retrieval | 2 | 6 | Vector recall + graph expand -> precise context, not file dumps.
v0.3 | 3 | Repo-graph tools | 2 | 7 | where_is / impact_of_change / risky_files / why-does-this-test-fail.
v0.3 | 3 | Memory | 2 | 5 | Explicit + episodic memory across nights, with user controls.
v0.3 | 3 | Independent reviewer | 1 | 3 | A different model reviews the writer's code — no self-grading.
v0.3 | 3 | Trigger engine | 2 | 7 | CI fails at 2am -> a fix plan waiting by morning, unqueued.
v0.3 | 3 | Observability (Langfuse) | 2 | 5 | Trace and replay exactly what the agent saw.
v0.4 | 4 | Personal mode + integrations | 2 | 10 | Gmail/Calendar/Notion + the chief-of-staff agent pool.
v0.4 | 4 | Local brain + mode isolation | 2 | 6 | Private comms on local Gemma; DB-enforced dev/personal split.
v0.4 | 4 | Full cost/rate governor | 2 | 6 | Forecast draw, surface '~3 left', per-mode budgets.
v0.4 | 4 | Eval / regression harness | 1 | 4 | Replay golden tasks to upgrade models/prompts with confidence.
v0.4 | 4 | Safety hardening | 3 | 10 | Two-key, privacy firewall, vault, command allowlist.
v0.4 | 4 | Voice (optional polish) | 1 | 3 | Whisper STT + Piper TTS for a spoken briefing.
v0.4 | 4 | Briefing + final acceptance | 2 | 6 | 7am briefing live; clean-machine setup from docs alone.
|  | TOTAL | 57 | 180 | 29 features across 4 versions / 4 weeks